🧾 Frontier AWS Migration – Cutover & UAT Plan (Enterprise Level)

1. Objective

Define the end-to-end migration and validation plan for Frontier application from on-prem Kyndryl servers to AWS Cloud, ensuring minimal downtime and full functional parity.

2. Scope

Covers all layers:

- AWS resource provisioning (VPCs, EC2s, RDS, FSxN, ALB/NLB, IAM)

- Application installation and configuration

- MFT, Tidal, Jenkins setup

- AD Connector and SSO integration

- Monitoring and logging setup

- UAT and cutover execution

3. Pre-Cutover Activities

| Activity | Owner | Description | Status |
| --- | --- | --- | --- |
| AWS account setup | Cloud Team | Create required AWS accounts and IAM roles | ✅ |
| VPC creation | Infra Team | Create two VPCs (Web Tier & App/Data Tier) with peering | ✅ |
| Security setup | Security Team | Configure SGs, NACLs, TLS certificates | ✅ |
| EC2 provisioning | Infra Team | Launch EC2s for Apache, App, Batch servers | ✅ |
| RDS setup | DBA Team | Create multi-AZ RDS SQL Server with shared connection string | ✅ |
| FSxN volumes | Storage Team | Create FSxN volumes for prod and archive data | ✅ |
| DRS setup | DR Team | Configure DRS agent for EBS snapshot replication | ✅ |
| Jenkins setup | DevOps Team | Install Jenkins, integrate with CyberArk for API key management | ✅ |
| MFT setup | Integration Team | Install Connect Direct service on app servers | ✅ |
| Tidal setup | Scheduler Team | Install Tidal agent on batch servers | ✅ |
| Monitoring setup | Ops Team | Configure CloudWatch, Dynatrace, Sumologic alerts, bat scripts for scheduler monitoring | ✅ |

4. Application Installation Session

- Vendor conducts installation on EC2 Windows app servers (Tomcat WAR deployment).

- Configure Apache reverse proxy and SSL offloading at ALB.

- Validate connectivity between Apache → NLB → App/Batch servers → RDS.

- Integrate AD Connector for SSO authentication.

- Validate FSxN shared storage access for session data and file transfers.

5. UAT Plan

| Phase | Description | Owner | Expected Outcome |
| --- | --- | --- | --- |
| Functional Testing | Validate all app modules and batch jobs | Business Users | All features work as expected |
| Performance Testing | Validate CPU/memory utilization under load | Infra Team | No degradation vs. on-prem |
| Security Testing | Validate AD group access, TLS, IAM roles | Security Team | All access controls enforced |
| Integration Testing | Validate MFT, Tidal, Jenkins, DB connectivity | Integration Team | All integrations successful |
| Failover Testing | Simulate EC2 failure and ASG recovery | Cloud Team | Auto-replacement within 5 min |
| DR Testing | Validate DRS snapshot replication and restore | DR Team | Successful EBS volume creation |

6. Cutover Plan

Timeline: Weekend window (3 hours downtime)

| Step | Description | Owner | Duration |
| --- | --- | --- | --- |
| 1 | Freeze on-prem changes | App Owner | 30 min |
| 2 | Final DB sync via AWS DMS | DBA Team | 30 min |
| 3 | Update DNS to point to ALB target group | Network Team | 15 min |
| 4 | Validate app connectivity and SSO | App Team | 30 min |
| 5 | Enable ASG and monitoring | Cloud Team | 15 min |
| 6 | Business smoke testing | Business Users | 30 min |
| 7 | Go/No-Go decision | Governance Team | 15 min |

Rollback Plan: If validation fails, disconnect new domain from ALB target group and revert DNS to on-prem environment.

7. Post-Cutover Validation

- Verify CloudWatch, Dynatrace, Sumologic alerts.

- Confirm FSxN data replication and access.

- Validate Jenkins pipeline deployment success.

- Confirm Tidal job execution and MFT transfers.

- Conduct DR replication test.

8. Documentation & Sign-Off

- UAT sign-off from business users (~40 testers).

- Cutover completion report.

- DR exercise report.

- Final governance approval.

9. Lessons Learned

- Shared storage solved session logout issue.

- Terraform modules ensured infra consistency.

- CyberArk + Ansible integration streamlined credential rotation.

- ASG improved resilience during traffic spikes.

📈 Future Enhancements

- Introduce Redis caching for read-heavy modules.

- Containerize batch jobs using EKS for better scalability.

- Integrate AWS Config for compliance tracking.